## comments
General Comments
A good start for the design
There is no system diagram, however documentation is ok.
Comments About Project Schedule (the one written in Open Project) (P.S. Penalties are written in red in parantheses)
Your detailed project plan (the one you prepared using Open Project) should have been updated as follows:
1. You should have revised your project plan so that it would include the submission of SDD, ODD, RAD,IUM,Database Design Document, Test Document & Standards and Quality Document (-30 pts -> -5 pts. for each document)
2. You should have made overall system design (system architecture level 0 and level 1) before designing database and web. This should have also been reflected to your project plan (-20 pts.)
In SUMMARY: REWRITE!!!!
Comments About Conformance to Plan
Below you can see your deliverables with the corresponding due dates set by you and our comments
Task | Due Date | Comments | Penalty
Database connection (11 days) | 04.11.2010 | 11 days is too long for database connection | -20 pts.
Template of Objective Question Type | 04.11.2010 | Too abstract, not specific enough. | -10 pts.
Template of Descriptive Question Type | 04.11.2010 | Too abstract, not specific enough. | -10 pts.
Environmental issues | 04.11.2010 | Not possible to understand what you mean. | -10 pts.
In SUMMARY: REWRITE!!!!